## Project info summary
RBSX Group Ltd Financial Investment and User Managment System
Key Project Info
Intended start Date | 2023-09-30
Requested time scale (Weeks) | 17
Requested time scale (Days) | 119
Hours worked per day per Staff member | 7
Predicted staff Absence (Days) | 0
Task | Estimated number of work hours | Staff member | Role | Key | Pay per hour
Upgrade infrastructure | 21 | Sarah O’Toole | Senior Software Engineer |  | 105
Install physical server | 7 | Ahad Shafiq | Junior Software Engineer |  | 25
Develop Module - Investments and savings | 115 | Terry Duran | Junior Software Engineer |  | 45
Develop Module - User interface | 70 | Gina Diaz | Database Engineer |  | 47.5
Develop Module - Information feed | 126 | Marius Bronski | Network Engineer |  | 73
Develop Module - Back-end database | 147
Develop Module - Data analytics | 112
Develop Module – Communications | 105
Deploy Modules | 7
(per module)
Unit testing | 21
(per module)
Integration testing | 14
(per module)
Fixing and regression testing for major fault | 14
(per fault found)
Fixing and regression testing for minor fault | 7
(per fault found)
User/acceptance testing | 35
Create a Test plan | 14
User Training | 21

## Gannt
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140 | 141 | 142 | 143 | 144 | 145 | 146 | 147 | 148 | 149 | 150 | 151 | 152 | 153 | 154 | 155 | 156
|  |  |  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday
 | time axis 2024-09-30 to 2025-03-04
Task | Sub Task/Notes | Staff assigned | Total hours assigned to task | 2025-01-26: Target completion date
Upgrade infrastructure |  | Marius Bronski | 21 | 2024-09-30: 7; 2024-10-01: 7; 2024-10-02: 7
Install physical server | Cloud server chosen – contingency time | Marius Bronski | 7 | 2024-10-03: 7
Develop Module - Back-end database | Phase 1 | Gina Diaz | 49 | 2024-09-30: 7; 2024-10-01: 7; 2024-10-02: 7; 2024-10-03: 7; 2024-10-04: 7; 2024-10-07: 7; 2024-10-08: 7
Unit testing | Test phase 1 | Gina Diaz | 7 | 2024-10-09: 7
Fixing and regression testing for minor fault | Database minor fault 1 | Gina Diaz | 7 | 2024-10-10: 7
Develop Module - Back-end database | Phase 2 | Gina Diaz | 49 | 2024-10-11: 7; 2024-10-14: 7; 2024-10-15: 7; 2024-10-16: 7; 2024-10-17: 7; 2024-10-18: 7; 2024-10-21: 7
Unit testing | Test phase 2 | Gina Diaz | 7 | 2024-10-22: 7
Fixing and regression testing for minor fault | Database minor fault 2 | Gina Diaz | 7 | 2024-10-23: 7
Develop Module - Back-end database | Phase 3 | Gina Diaz | 49 | 2024-10-24: 7; 2024-10-25: 7; 2024-10-28: 7; 2024-10-29: 7; 2024-10-30: 7; 2024-10-31: 7; 2024-11-01: 7
Unit testing | Test phase 3 | Gina Diaz | 7 | 2024-11-04: 7
Fixing and regression testing for minor fault | Database minor fault 3 | Gina Diaz | 7 | 2024-11-05: 7
Develop Module - Investments and savings | Phase 1 | Sarah O’Toole | 35 | 2024-09-30: 7; 2024-10-01: 7; 2024-10-02: 7; 2024-10-03: 7; 2024-10-04: 7
Unit testing | Test Phase 1 | Sarah O’Toole | 7 | 2024-10-07: 7
Fixing and regression testing for minor fault | Investments minor fault 1 | Sarah O’Toole | 7 | 2024-10-08: 7
Develop Module - Investments and savings | Phase 2 | Sarah O’Toole | 42 | 2024-10-09: 7; 2024-10-10: 7; 2024-10-11: 7; 2024-10-14: 7; 2024-10-15: 7; 2024-10-16: 7
Unit testing | Test Phase 2 | Sarah O’Toole | 7 | 2024-10-17: 7
Fixing and regression testing for minor fault | Investments minor fault 2 | Sarah O’Toole | 7 | 2024-10-18: 7
Develop Module - Investments and savings | Phase 3 | Sarah O’Toole | 42 | 2024-10-21: 7; 2024-10-22: 7; 2024-10-23: 7; 2024-10-24: 7; 2024-10-25: 7; 2024-10-28: 7
Unit testing | Test Phase 3 | Sarah O’Toole | 7 | 2024-10-29: 7
Fixing and regression testing for minor fault | Investments minor fault 3 | Sarah O’Toole | 7 | 2024-10-30: 7
Integration testing | Investments and Database | Sarah O’Toole | 28 | 2024-11-04: 7; 2024-11-05: 7; 2024-11-06: 7; 2024-11-07: 7
Fixing and regression testing for major fault | Predicted Major fault 1 | Sarah O’Toole | 14 | 2024-11-08: 7; 2024-11-11: 7
Fixing and regression testing for major fault | Predicted Major fault 1 | Gina Diaz | 14 | 2024-11-08: 7; 2024-11-11: 7
Deploy Modules | Deploy database and investments | Terry Duran | 14 | 2024-11-08: 7; 2024-11-11: 7
Develop Module - Data analytics | Phase 1 | Gina Diaz | 35 | 2024-11-12: 7; 2024-11-13: 7; 2024-11-14: 7; 2024-11-15: 7; 2024-11-18: 7
Unit testing | Test Phase 1 | Gina Diaz | 7 | 2024-11-19: 7
Fixing and regression testing for minor fault | Analytics Minor Fault 1 | Gina Diaz | 7 | 2024-11-20: 7
Develop Module - Data analytics | Phase 2 | Gina Diaz | 35 | 2024-11-21: 7; 2024-11-22: 7; 2024-11-25: 7; 2024-11-26: 7; 2024-11-27: 7
Unit testing | Test Phase 2 | Gina Diaz | 7 | 2024-11-28: 7
Fixing and regression testing for minor fault | Analytics Minor Fault 2 | Gina Diaz | 7 | 2024-11-29: 7
Develop Module - Data analytics | Phase 3 | Gina Diaz | 35 | 2024-12-02: 7; 2024-12-03: 7; 2024-12-04: 7; 2024-12-05: 7; 2024-12-06: 7
Unit testing | Test Phase 3 | Gina Diaz | 7 | 2024-12-09: 7
Fixing and regression testing for minor fault | Analytics Minor Fault 3 | Gina Diaz | 7 | 2024-12-10: 7
Integration testing | integrate analytics | Gina Diaz | 14 | 2024-12-11: 7; 2024-12-12: 7
Deploy Modules | Deploy analytics | Gina Diaz | 7 | 2024-12-13: 7
Develop Module - Information feed | Phase 1 | Ahad Shafiq | 42 | 2024-11-12: 7; 2024-11-13: 7; 2024-11-14: 7; 2024-11-15: 7; 2024-11-18: 7; 2024-11-19: 7
Develop Module - Information feed | Phase 1 | Terry Duran | 42 | 2024-11-12: 7; 2024-11-13: 7; 2024-11-14: 7; 2024-11-15: 7; 2024-11-18: 7; 2024-11-19: 7
Unit testing | Test Phase 1 | Ahad Shafiq | 7 | 2024-11-20: 7
Unit testing | Test Phase 1 | Terry Duran | 7 | 2024-11-20: 7
Fixing and regression testing for minor fault | Information feed minor fault 1 | Ahad Shafiq | 7 | 2024-11-21: 7
Fixing and regression testing for minor fault | Information feed minor fault 1 | Terry Duran | 7 | 2024-11-21: 7
Develop Module - Information feed | Phase 2 | Ahad Shafiq | 42 | 2024-11-22: 7; 2024-11-25: 7; 2024-11-26: 7; 2024-11-27: 7; 2024-11-28: 7; 2024-11-29: 7
Develop Module - Information feed | Phase 2 | Terry Duran | 42 | 2024-11-22: 7; 2024-11-25: 7; 2024-11-26: 7; 2024-11-27: 7; 2024-11-28: 7; 2024-11-29: 7
Unit testing | Test Phase 2 | Ahad Shafiq | 7 | 2024-12-02: 7
Unit testing | Test Phase 2 | Terry Duran | 7 | 2024-12-02: 7
Fixing and regression testing for minor fault | Information feed minor fault 2 | Ahad Shafiq | 7 | 2024-12-03: 7
Fixing and regression testing for minor fault | Information feed minor fault 2 | Terry Duran | 7 | 2024-12-03: 7
Develop Module - Information feed | Phase 3 | Ahad Shafiq | 42 | 2024-12-04: 7; 2024-12-05: 7; 2024-12-06: 7; 2024-12-07: 7; 2024-12-08: 7; 2024-12-09: 7
Develop Module - Information feed | Phase 3 | Terry Duran | 42 | 2024-12-04: 7; 2024-12-05: 7; 2024-12-06: 7; 2024-12-07: 7; 2024-12-08: 7; 2024-12-09: 7
Unit testing | Test Phase 3 | Ahad Shafiq | 7 | 2024-12-10: 7
Unit testing | Test Phase 3 | Terry Duran | 7 | 2024-12-10: 7
Fixing and regression testing for minor fault | Information feed minor fault 3 | Ahad Shafiq | 7 | 2024-12-11: 7
Fixing and regression testing for minor fault | Information feed minor fault 3 | Terry Duran | 7 | 2024-12-11: 7
Integration testing | Integrate Info feed with rest of system | Ahad Shafiq | 14 | 2024-12-12: 7; 2024-12-13: 7
Integration testing |  | Terry Duran | 14 | 2024-12-12: 7; 2024-12-13: 7
Deploy Modules | Deploy info feed | Ahad Shafiq | 7 | 2024-12-16: 7
Deploy Modules |  | Terry Duran | 7 | 2024-12-16: 7
Develop Module – Communications | Phase 1 | Sarah O’Toole | 35 | 2024-11-12: 7; 2024-11-13: 7; 2024-11-14: 7; 2024-11-15: 7; 2024-11-18: 7
Unit testing | Test Phase 1 | Sarah O’Toole | 7 | 2024-11-19: 7
Fixing and regression testing for minor fault | Comms minor fault 1 | Sarah O’Toole | 7 | 2024-11-20: 7
Develop Module – Communications | Phase 2 | Sarah O’Toole | 35 | 2024-11-21: 7; 2024-11-22: 7; 2024-11-25: 7; 2024-11-26: 7; 2024-11-27: 7
Unit testing | Test Phase 2 | Sarah O’Toole | 7 | 2024-11-28: 7
Fixing and regression testing for minor fault | Comms minor fault 2 | Sarah O’Toole | 7 | 2024-11-29: 7
Develop Module – Communications | Phase 3 | Sarah O’Toole | 35 | 2024-12-02: 7; 2024-12-03: 7; 2024-12-04: 7; 2024-12-05: 7; 2024-12-06: 7
Unit testing | Test Phase 3 | Sarah O’Toole | 7 | 2024-12-09: 7
Fixing and regression testing for minor fault | Comms minor fault 3 | Sarah O’Toole | 7 | 2024-12-10: 7
Integration testing | Integrate Comms | Sarah O’Toole | 14 | 2024-12-11: 7; 2024-12-12: 7
Deploy Modules | Deploy comms | Sarah O’Toole | 7 | 2024-12-13: 7
Fixing and regression testing for major fault | Predicted major fault 2 | Sarah O’Toole | 14 | 2024-12-16: 7; 2024-12-17: 7
Fixing and regression testing for major fault | Predicted major fault 2 | Gina Diaz | 14 | 2024-12-16: 7; 2024-12-17: 7
Develop Module - User interface | Phase 1 | Sarah O’Toole | 21 | 2024-12-18: 7; 2024-12-19: 7; 2024-12-20: 7
Develop Module - User interface | Phase 1 | Ahad Shafiq | 21 | 2024-12-18: 7; 2024-12-19: 7; 2024-12-20: 7
Unit testing | UI test Phase 1 | Sarah O’Toole | 7 | 2024-12-23: 7
Unit testing | UI Test Phase 1 | Ahad Shafiq | 7 | 2024-12-23: 7
Fixing and regression testing for minor fault | UI Minor Fault 1 | Sarah O’Toole | 7 | 2024-12-24: 7
Fixing and regression testing for minor fault | UI Minor Fault 1 | Ahad Shafiq | 7 | 2024-12-24: 7
Develop Module - User interface | Phase 2 | Sarah O’Toole | 21 | 2024-12-25: 7; 2024-12-26: 7; 2024-12-27: 7
Develop Module - User interface | Phase 2 | Ahad Shafiq | 21 | 2024-12-25: 7; 2024-12-26: 7; 2024-12-27: 7
Unit testing | UI test Phase 2 | Sarah O’Toole | 7 | 2024-12-30: 7
Unit testing | UI Test Phase 2 | Ahad Shafiq | 7 | 2024-12-30: 7
Fixing and regression testing for minor fault | UI Minor Fault 2 | Sarah O’Toole | 7 | 2024-12-31: 7
Fixing and regression testing for minor fault | UI Minor Fault 2 | Ahad Shafiq | 7 | 2024-12-31: 7
Develop Module - User interface | Phase 3 | Sarah O’Toole | 28 | 2025-01-01: 7; 2025-01-02: 7; 2025-01-03: 7; 2025-01-06: 7
Develop Module - User interface | Phase 3 | Ahad Shafiq | 28 | 2025-01-01: 7; 2025-01-02: 7; 2025-01-03: 7; 2025-01-06: 7
Unit testing | UI test Phase 3 | Sarah O’Toole | 7 | 2025-01-07: 7
Unit testing | UI Test Phase 3 | Ahad Shafiq | 7 | 2025-01-07: 7
Fixing and regression testing for minor fault | UI Minor Fault 3 | Sarah O’Toole | 7 | 2025-01-08: 7
Fixing and regression testing for minor fault | UI Minor Fault 3 | Ahad Shafiq | 7 | 2025-01-08: 7
Integration testing | integrate UI | Sarah O’Toole | 14 | 2025-01-09: 7; 2025-01-10: 7
Deploy Modules | Deploy UI | Sarah O’Toole | 7 | 2025-01-13: 7
Fixing and regression testing for major fault | Predicted major fault 3 | Sarah O’Toole | 14 | 2025-01-14: 7; 2025-01-15: 7
User Training |  | Sarah O’Toole | 21 | 2025-01-16: 7; 2025-01-17: 7; 2025-01-20: 7
User/acceptance testing |  | Terry Duran | 35 | 2025-01-16: 7; 2025-01-17: 7; 2025-01-20: 7; 2025-01-22: 7; 2025-01-23: 7
Create a Test plan |  | Terry Duran | 14 | 2024-09-30: 7; 2024-10-01: 7
| Project manager |  | 588 | 2024-09-30: 7; 2024-10-01: 7; 2024-10-02: 7; 2024-10-03: 7; 2024-10-04: 7; 2024-10-07: 7; 2024-10-08: 7; 2024-10-09: 7; 2024-10-10: 7; 2024-10-11: 7; 2024-10-14: 7; 2024-10-15: 7; 2024-10-16: 7; 2024-10-17: 7; 2024-10-18: 7; 2024-10-21: 7; 2024-10-22: 7; 2024-10-23: 7; 2024-10-24: 7; 2024-10-25: 7; 2024-10-28: 7; 2024-10-29: 7; 2024-10-30: 7; 2024-10-31: 7; 2024-11-01: 7; 2024-11-04: 7; 2024-11-05: 7; 2024-11-06: 7; 2024-11-07: 7; 2024-11-08: 7; 2024-11-11: 7; 2024-11-12: 7; 2024-11-13: 7; 2024-11-14: 7; 2024-11-15: 7; 2024-11-18: 7; 2024-11-19: 7; 2024-11-20: 7; 2024-11-21: 7; 2024-11-22: 7; 2024-11-25: 7; 2024-11-26: 7; 2024-11-27: 7; 2024-11-28: 7; 2024-11-29: 7; 2024-12-02: 7; 2024-12-03: 7; 2024-12-04: 7; 2024-12-05: 7; 2024-12-06: 7; 2024-12-09: 7; 2024-12-10: 7; 2024-12-11: 7; 2024-12-12: 7; 2024-12-13: 7; 2024-12-16: 7; 2024-12-17: 7; 2024-12-18: 7; 2024-12-19: 7; 2024-12-20: 7; 2024-12-23: 7; 2024-12-24: 7; 2024-12-25: 7; 2024-12-26: 7; 2024-12-27: 7; 2024-12-30: 7; 2024-12-31: 7; 2025-01-01: 7; 2025-01-02: 7; 2025-01-03: 7; 2025-01-06: 7; 2025-01-07: 7; 2025-01-08: 7; 2025-01-09: 7; 2025-01-10: 7; 2025-01-13: 7; 2025-01-14: 7; 2025-01-15: 7; 2025-01-16: 7; 2025-01-17: 7; 2025-01-20: 7; 2025-01-21: 7; 2025-01-22: 7; 2025-01-23: 7
0
Note on B23: Slightly over allocated i time (Contingency)
Note on B36: Very slightly over allocated (3 hours)

## Costs
Staff Costs
Staff | Hours worked | Rate of pay | Cost for project | Current Income | 1580900
Sarah O’Toole | 553 | 105 | 58065 | Current outgoings | 985340
Ahad Shafiq | 301 | 25 | 7525
Terry Duran | 252 | 45 | 11340
Gina Diaz | 385 | 47.5 | 18287.5
Marius Bronski | 28 | 73 | 2044
Project manager | 84 | 200 | 16800
Project Costs |  |  |  | Forecast With Solution
Item | Costs | QTY | Subtotal |  | Current year | After 1 year | After 2 year | After 3 years
Software development company base fee | 50000 | 1 | 50000 | Current Income | 1580900 | 1719228.75 | 1985709.2063 | 2243851.4031
Cost of training and development of internal staff | 4000 | 1 | 4000 | Current outgoings | 985340 | 985340 | 985340 | 985340
Cost of equipment upgrades (laptops, work stations, etc.) | 15000 | 1 | 15000 | One-off costs | 103000
Cost of software licensing | 4000 | 1 | 4000 | Ongoing costs | 41210 | 41210 | 41210 | 41210
Cost of new server (cloud) | 830 | 12 | 9960 | Total costs | 1129550 | 1026550 | 1026550 | 1026550
Cost of infrastructure (networking) upgrades | 13200 | 1 | 13200 | Profit/Loss (Inc. Carry forward) | 451350 | 1144028.75 | 2103187.9562 | 3320489.3593
|  | Subtotal | 96160
Ongoing costs
Additional network technician | 22000
Maintenance costs (server, equipment, infrastructure) | 9250