## Project info summary
RBSX Group Ltd Financial Investment and User Managment System
Key Project Info
Intended start Date | 2023-09-30
Requested time scale (Weeks) | 17
Requested time scale (Days) | 119
Hours worked per day per Staff member | 7
Predicted staff Abscence (Days) | 0
Task | Estimated number of work hours | Staff member | Role | Key | Pay per hour
Upgrade infrastructure | 21 | Sarah O’Toole | Senior Software Engineer |  | 105
Install physical server | 7 | Ahad Shafiq | Junior Software Engineer |  | 25
Develop Module - Investments and savings | 115 | Terry Duran | Junior Software Engineer |  | 45
Develop Module - User interface | 70 | Gina Diaz | Database Engineer |  | 47.5
Develop Module - Information feed | 126 | Marius Bronski | Network Engineer |  | 73
Develop Module - Back-end database | 147
Develop Module - Data analytics | 112
Develop Module – Communications | 105
Deploy Modules | 7
(per module)
Unit testing | 21
(per module)
Integration testing | 14
(per module)
Fixing and regression testing for major fault | 14
(per fault found)
Fixing and regression testing for minor fault | 7
(per fault found)
User/acceptance testing | 35
Create a Test plan | 14
User Training | 21

## Gannt
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140 | 141 | 142 | 143 | 144 | 145 | 146 | 147 | 148 | 149 | 150 | 151 | 152 | 153 | 154 | 155 | 156
|  |  |  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday
 | time axis 2024-09-30 to 2025-03-04
Task | Sub Task/Notes | Staff assigned | Total hours assigned to task
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Costs
Staf Costs
Staff | Hours worked | Rate of pay | Cost for project
Sarah O’Toole | 0 | 105 | 0
Ahad Shafiq | 0 | 25 | 0
Terry Duran | 0 | 45 | 0
Gina Diaz | 0 | 47.5 | 0
Marius Bronski | 0 | 73 | 0

## Copyright
T Level Technical Qualification in Digital Software Development (Level 3)
Employer-set Project
Task 1 RBSX Project Plan
Candidate surname | xx
Other names | xx
Centre number | xx
Learner ID | xx
Copyright and Acknowledgements
‘T-LEVELS’ is a registered trade mark of the Department for Education.
‘T Level’ is a registered trade mark of the Institute for Apprenticeships and Technical Education.
The T Level Technical Qualification is a qualification approved and managed by the Institute for Apprenticeships and Technical Education.
‘Institute for Apprenticeships & Technical Education’ and logo are registered trade marks of the Institute for Apprenticeships and Technical Education.
Pearson Education Limited is authorised by the Institute for Apprenticeships and Technical Education to develop and deliver this Technical Qualification.
Pearson and logo are registered trade marks of Pearson.
Copyright in this document belongs to, and is used under licence from, the Institute for Apprenticeships and Technical Education, © 2025
Version 1.1 - July 2025