## Project info summary
RetailX Group Ltd Digital Solution
Key Project Info
Intended start Date | 2025-01-05
Requested time scale (Weeks) | 18
Requested time scale (Days) | 126
Hours worked per day per Staff member | 8
Predicted staff Absence (Days) | 14
Task | Estimated number of work hours | Staff member | Role | Key | Pay per hour
Upgrade infrastructure | 72 | Priya Patel | Senior Software Engineer |  | 110
Install physical server | 24 | Alex Morgan | Junior Software Engineer |  | 38
Deploy and configure cloud server | 20 | Samir Khan | Junior Software Engineer |  | 47
Develop module – Stock and inventory management | 108 | Jamie Lee | Database Engineer |  | 52
Develop module - User interface | 65 | Morgan Evans | Network Engineer |  | 78
Develop module – Customer management and rewards | 142
Develop module - Back-end database | 120
Develop module - Sales analysis | 100
Deploy modules | 8 (per module)
Unit testing | 21 (per module)
Integration testing | 14 (per module)
Fixing and regression testing for major fault | 21 (per fault found)
Fixing and regression testing for minor fault | 10 (per fault found)
Deploy and configure cloud backup system | 20
User/acceptance testing | 35
Create a test plan | 21
Training RetailX staff to use new system | 34
Update website | 40
Build and deploy customer rewards app | 50
Hardware testing | 30

## Gantt
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140 | 141 | 142 | 143 | 144 | 145 | 146 | 147 | 148 | 149 | 150 | 151 | 152 | 153 | 154
|  |  |  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
 | time axis 2025-01-05 to 2025-06-07
Task | Sub Task/Notes | Staff assigned | Total hours assigned to task
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Costs
Staf Costs
Staff | Hours worked | Rate of pay | Cost for project
Priya Patel | 0 | 110 | 0
Alex Morgan | 0 | 38 | 0
Samir Khan | 0 | 47 | 0
Jamie Lee | 0 | 52 | 0
Morgan Evans | 0 | 78 | 0

## Copyright
T Level Technical Qualification in Digital Software Development (Level 3)
Employer Set Project
Task 1 RetailX Project Plan
Candidate surname | xx
Other names | xx
Centre number | xx
Learner ID | xx
Copyright and Acknowledgements
Copyright in this document belongs to, and is used under licence from the Department for Education, © 2025.
‘T-LEVELS’ and ‘T Level’ are registered trademarks of the Department for Education. Pearson is authorised by the Department for Education to develop and deliver this T Level Technical Qualification.
Pearson and logo are registered trademarks of Pearson.
Version 1.0 - October 2025